## Risk Register
Apex Financial Services — Cybersecurity Risk Register
Portfolio Project ¦ Fictional Company ¦ Risk scoring uses Likelihood × Impact (1–5)
R-001 | Phishing & Credential Theft | Employee email accounts | Credential phishing | Limited phishing awareness; users may click malicious links | 4 | 5 | MFA; email filtering; security awareness training | Mitigate | Phishing simulations; strengthen email filtering; enforce phishing-resistant MFA for privileged users | IT Security Manager | 2 | 4 | Open | 2026-10-15
R-002 | Ransomware Infection | Endpoints and file shares | Ransomware | Unpatched endpoints; malicious attachments; excessive endpoint privileges | 4 | 5 | Endpoint protection; backups; patching process | Mitigate | EDR tuning; offline/immutable backups; application allowlisting; tabletop exercise | IT Security Manager | 2 | 4 | Open | 2026-11-01
R-003 | Unpatched Critical Systems | Servers and workstations | Exploitation of known vulnerabilities | Delayed patch deployment and incomplete asset inventory | 4 | 4 | Monthly patch cycle; vulnerability scanning | Mitigate | Risk-based patch SLAs; automated deployment; asset inventory reconciliation | IT Operations Manager | 2 | 3 | In Progress | 2026-09-30
R-004 | Excessive User Privileges | Identity and access management | Privilege abuse | Users retain access after role changes; weak access reviews | 3 | 5 | Role-based access; manager approvals | Mitigate | Quarterly access reviews; least privilege; privileged access management | IAM Manager | 2 | 4 | Open | 2026-10-31
R-005 | Third-Party Vendor Breach | Vendor-managed systems/data | Compromise of service provider | Inconsistent vendor security assessments and contract requirements | 3 | 5 | Vendor contracts; basic due diligence | Mitigate | Annual vendor risk assessments; security clauses; breach notification requirements | GRC Manager | 2 | 4 | Open | 2026-11-15
R-006 | Data Loss / Accidental Disclosure | Customer and employee data | Unauthorized disclosure | Sensitive data stored or shared without consistent classification | 3 | 5 | Access controls; encryption; backups | Mitigate | Data classification policy; DLP controls; secure sharing standards | Privacy Officer | 2 | 4 | Open | 2026-10-31
R-007 | Weak Passwords / Authentication | Corporate applications | Account takeover | Password reuse; inconsistent MFA coverage | 4 | 4 | Password policy; MFA on critical systems | Mitigate | Expand MFA; SSO; password manager; monitor compromised credentials | IAM Manager | 2 | 3 | In Progress | 2026-09-15
R-008 | Insider Threat | Corporate systems and data | Malicious or negligent insider | Limited behavioral monitoring; broad access to sensitive data | 2 | 5 | HR onboarding/offboarding; access controls | Mitigate | UEBA; enhanced logging; least privilege; separation of duties | IT Security Manager | 1 | 4 | Open | 2026-12-01
R-009 | Cloud Misconfiguration | Cloud storage and services | Unauthorized access | Inconsistent security configuration and monitoring | 3 | 5 | Cloud IAM; baseline configurations | Mitigate | CSPM; configuration baselines; continuous monitoring; secure architecture reviews | Cloud Operations Manager | 2 | 4 | Open | 2026-11-30
R-010 | Insufficient Security Logging | Critical applications and infrastructure | Delayed detection | Logs not centralized; inconsistent retention and alerting | 3 | 4 | System logs; limited centralized monitoring | Mitigate | SIEM onboarding; log retention standard; alert use cases; daily monitoring | SOC Manager | 1 | 3 | In Progress | 2026-10-15
R-011 | Business Email Compromise | Finance and executive email | Social engineering / account compromise | Weak payment verification; exposed executive accounts | 3 | 5 | MFA; approval workflows | Mitigate | Out-of-band payment verification; executive protection; conditional access | Finance Director | 2 | 4 | Open | 2026-10-31
R-012 | Lost or Stolen Device | Laptops and mobile devices | Physical theft | Device may contain cached data; inconsistent encryption | 3 | 4 | Endpoint encryption; device inventory | Mitigate | Enforce full-disk encryption; MDM; remote wipe; asset tracking | IT Operations Manager | 1 | 3 | In Progress | 2026-09-30
R-013 | Backup Failure | Critical business data | Data unrecoverability | Backups may fail or not be tested regularly | 2 | 5 | Scheduled backups; backup monitoring | Mitigate | Quarterly restore tests; immutable backup copies; documented RTO/RPO | Infrastructure Manager | 1 | 3 | Open | 2026-10-31
R-014 | Unsupported Software | Endpoints and applications | Exploitation / instability | Legacy applications beyond vendor support lifecycle | 3 | 4 | Software inventory; limited compensating controls | Mitigate | Application lifecycle plan; replacement roadmap; network isolation where needed | IT Operations Manager | 2 | 3 | Open | 2027-01-15
R-015 | Incident Response Gaps | Security operations | Slow or inconsistent response | Incomplete playbooks; limited tabletop testing | 3 | 4 | Incident response policy; escalation contacts | Mitigate | Create playbooks; tabletop exercises; after-action reviews; define SLAs | SOC Manager | 1 | 3 | Open | 2026-11-15

## Risk Methodology
Apex Financial Services — Risk Assessment Methodology
Purpose | Provide a repeatable approach for identifying, rating, treating, and monitoring cybersecurity risks.
Scope | Fictional corporate environment covering identity, endpoints, cloud, vendors, data, infrastructure, and security operations.
Likelihood | 1 = Rare ¦ 2 = Unlikely ¦ 3 = Possible ¦ 4 = Likely ¦ 5 = Almost Certain
Impact | 1 = Negligible ¦ 2 = Minor ¦ 3 = Moderate ¦ 4 = Major ¦ 5 = Severe
Risk Score | Likelihood × Impact
Low | 1–4
Medium | 5–9
High | 10–14
Critical | 15–25
Risk Treatment | Mitigate = reduce likelihood/impact; Transfer = shift financial/contractual exposure; Accept = formally retain risk; Avoid = stop the risky activity.
Residual Risk | Risk remaining after existing and recommended controls are considered.

## Executive Summary
Apex Financial Services — Executive Risk Summary
Project Type | Cybersecurity / GRC Portfolio Project
Assessment Date | 2026-08-14
Total Risks | 15
Critical Inherent Risks
High Inherent Risks
Medium Inherent Risks
Low Inherent Risks
Priority Findings
1 | Phishing, ransomware, and credential compromise create the greatest immediate exposure.
2 | Identity and access controls should be strengthened through least privilege, MFA, and recurring access reviews.
3 | Patch management, logging/SIEM coverage, and incident response readiness require continued investment.
4 | Third-party and cloud risks require consistent assessments and configuration monitoring.
Recommended Next Steps
1 | Address Critical and High risks first with named owners and target dates.
2 | Track residual risk after controls are implemented.
3 | Review the register at least quarterly and after major security incidents or technology changes.